|  |  |  |
| --- | --- | --- |
| **Task/Initiative** | **Proposed timeframe** | **Logistics** |
| 1. Introduction – Creating school awareness
 | End of term 2 | * Staff meeting to introduce project
* Student competition (creating signs for classrooms for composting, recycling and rubbish facts)
 |
| 1. Composting and paper recycling
 | Start of term 3 | * First week assembly presentation from ‘green team’
* Staff meeting presentation (by green team)
* Compost bins and recycling box to be placed in each class room
* Student monitors collect Wednesday and Friday afternoons
* Presentation at weekly assembly for best class
 |
| 1. Celebration of recycling, composting
 | Term 4 | * Prize for class who has demonstrated great commitment to cause
* Report success in newsletter etc
 |
| 1. Going to nude lunches
 | End of Term 4Term 1 | * Introduce next phase to reduce school waste by assembly presentation, in newsletter and staff meeting
* Recap with students and start
* Prizes for class who produce the least amount of waste
 |